## Launch Checklist
Phase | Category | Task | Owner | Priority | Status | Start Date | Due Date | Notes
Pre-Launch | Business Foundation | Define T-shirt niche and target audience | Founder | High | Not Started | 2025-09-02 | 2025-09-05 | Focus on unique designs or specific customer segments
Pre-Launch | Business Foundation | Conduct market research and competitor analysis | Marketing Lead | High | Not Started | 2025-09-02 | 2025-09-10 | Analyze trends, pricing, and gaps in market
Pre-Launch | Business Foundation | Create business plan and financial projections | Founder | High | Not Started | 2025-09-05 | 2025-09-12 | Include revenue goals and cost structure
Pre-Launch | Business Foundation | Register business and obtain necessary licenses | Founder | High | Not Started | 2025-09-08 | 2025-09-15 | GST registration, business registration
Pre-Launch | Product Development | Design T-shirt and Polo graphics/concepts | Designer | High | Not Started | 2025-09-10 | 2025-09-20 | Create 10-15 initial designs
Pre-Launch | Product Development | Source and vet dropshipping suppliers | Operations | High | Not Started | 2025-09-12 | 2025-09-22 | Get samples, check quality and reliability
Pre-Launch | Product Development | Create product mockups and size guides | Designer | Medium | Not Started | 2025-09-18 | 2025-09-25 | Professional product photography style
Pre-Launch | Product Development | Finalize product catalog and pricing | Founder | High | Not Started | 2025-09-22 | 2025-09-28 | Competitive pricing with profit margins
Pre-Launch | Branding | Develop brand name and positioning statement | Marketing Lead | High | Not Started | 2025-09-02 | 2025-09-08 | Clear brand identity and values
Pre-Launch | Branding | Design logo and brand assets | Designer | High | Not Started | 2025-09-08 | 2025-09-15 | Logo, color palette, typography
Pre-Launch | Branding | Create brand guidelines document | Designer | Medium | Not Started | 2025-09-15 | 2025-09-20 | Consistent brand application
Pre-Launch | Website Setup | Choose e-commerce platform (Shopify/WooCommerce) | Tech Lead | High | Not Started | 2025-09-15 | 2025-09-18 | Consider features, costs, scalability
Pre-Launch | Website Setup | Register domain name | Tech Lead | High | Not Started | 2025-09-15 | 2025-09-17 | Brand-relevant domain
Pre-Launch | Website Setup | Design and build online store | Tech Lead | High | Not Started | 2025-09-18 | 2025-10-02 | Mobile-responsive, user-friendly
Pre-Launch | Website Setup | Create compelling product listings | Marketing Lead | High | Not Started | 2025-09-25 | 2025-10-05 | SEO-optimized descriptions, high-quality images
Pre-Launch | Website Setup | Set up payment gateways | Tech Lead | High | Not Started | 2025-09-28 | 2025-10-02 | Multiple secure payment options
Pre-Launch | Website Setup | Configure shipping and tax settings | Operations | High | Not Started | 2025-09-30 | 2025-10-03 | Accurate shipping rates and tax calculations
Pre-Launch | Legal | Create terms of service and privacy policy | Founder | High | Not Started | 2025-09-20 | 2025-09-25 | Legal compliance for e-commerce
Pre-Launch | Legal | Set up business insurance | Founder | Medium | Not Started | 2025-09-25 | 2025-10-01 | Product liability and business insurance
Pre-Launch | Marketing Prep | Develop marketing strategy and calendar | Marketing Lead | High | Not Started | 2025-09-20 | 2025-09-28 | Multi-channel approach
Pre-Launch | Marketing Prep | Create social media profiles | Marketing Lead | High | Not Started | 2025-09-22 | 2025-09-26 | Instagram, Facebook, TikTok, Pinterest
Pre-Launch | Marketing Prep | Design marketing materials | Designer | Medium | Not Started | 2025-09-25 | 2025-10-02 | Social media graphics, email templates
Pre-Launch | Marketing Prep | Set up email marketing system | Marketing Lead | Medium | Not Started | 2025-09-28 | 2025-10-03 | Mailchimp or similar platform
Pre-Launch | Marketing Prep | Plan influencer outreach campaign | Marketing Lead | Medium | Not Started | 2025-09-30 | 2025-10-05 | Identify and contact relevant influencers
Pre-Launch | Testing | Test complete shopping experience | Tech Lead | High | Not Started | 2025-10-03 | 2025-10-06 | End-to-end user journey testing
Pre-Launch | Testing | Set up analytics and tracking | Tech Lead | High | Not Started | 2025-10-01 | 2025-10-04 | Google Analytics, Facebook Pixel
Pre-Launch | Testing | Create customer support processes | Operations | High | Not Started | 2025-10-02 | 2025-10-06 | FAQ, support email, chat system
Pre-Launch | Testing | Conduct soft launch with friends/family | Founder | Medium | Not Started | 2025-10-05 | 2025-10-08 | Gather feedback and fix issues
Launch | Launch Execution | Execute launch marketing campaign | Marketing Lead | High | Not Started | 2025-10-10 | 2025-10-10 | Coordinated social media, email, PR push
Launch | Launch Execution | Monitor website performance and sales | Tech Lead | High | Not Started | 2025-10-10 | 2025-10-17 | Real-time monitoring for issues
Launch | Launch Execution | Respond to customer inquiries promptly | Operations | High | Not Started | 2025-10-10 | Ongoing | Maintain high customer service standards
Launch | Launch Execution | Track key performance metrics | Founder | High | Not Started | 2025-10-10 | Ongoing | Sales, traffic, conversion rates
Post-Launch | Optimization | Analyze launch performance data | Marketing Lead | High | Not Started | 2025-10-17 | 2025-10-20 | Identify successful and unsuccessful elements
Post-Launch | Optimization | Collect and analyze customer feedback | Operations | High | Not Started | 2025-10-15 | 2025-10-25 | Surveys, reviews, direct feedback
Post-Launch | Optimization | Optimize website based on user behavior | Tech Lead | Medium | Not Started | 2025-10-20 | 2025-10-30 | Improve conversion rates and user experience
Post-Launch | Optimization | Refine marketing campaigns | Marketing Lead | Medium | Not Started | 2025-10-18 | 2025-10-28 | Focus budget on best-performing channels
Post-Launch | Optimization | Plan next product releases | Designer | Medium | Not Started | 2025-10-25 | 2025-11-05 | New designs based on customer preferences
Growth | Scaling | Implement customer retention strategies | Marketing Lead | Medium | Not Started | 2025-11-01 | 2025-11-15 | Loyalty programs, email campaigns
Growth | Scaling | Explore additional sales channels | Founder | Medium | Not Started | 2025-11-10 | 2025-11-25 | Amazon, Etsy, other marketplaces
Growth | Scaling | Analyze and expand product line | Founder | Medium | Not Started | 2025-11-15 | 2025-12-01 | Add complementary products
Growth | Scaling | Consider international expansion | Founder | Low | Not Started | 2025-12-01 | 2025-12-31 | Assess viability of global shipping